## Sheet1
Infoconnect Monitoring Utilizing Site 24X7
DEV |  |  |  |  | QA | QA
Pages | Screen/View/Feature | Task | Requirement Understanding/Queries | FET (In HRS) | Test Design (In HRS) | Testing (In HRS) | Cross Browser testing (In HRS)
Monitoring Dashboard | Monitor Heirarchy | Design data structure | Sequence for hierarchy is considered as per BRD and will be static but configurable. | 8 | NA | NA | NA
|  | Display tree |  | 16 | 2 | 4 | 16
|  | Display module monitor list on hover with status buttons (Up/Down). |  | 16 | 4 | 4 | 16
|  | Highlight node links as per status |  | 16 | 2 | 4 | 16
Client Facing Dashboard | Infoconnect Status Page | Page Layout | Reference: https://status.apigee.com/ | 8 | 4 | 16 | 64
|  | Populate data from 24X7 API |  | 16 | 4 | 16 | 64
|  | Requirement Understanding |  | 4 | 1 | 8 | NA
|  | Site 24X7 API Review |  | 12 | 1 | 8 | NA
|  | Integration Effort | Need more info on page integration. | 16 | NA | NA | NA
|  | Total Efforts (hrs) |  | 112 | 18 | 60 | 176
|  | Total Efforts (days) |  | 14 | 31.75
Notes, Assumptions Frontend Development:
Estimation assumes HTML, CSS and JavaScript development only.
Analytics dashboard (Bar and Pie charts) is not considered for estimates as per discussion.
Estimated screens will not be responsive. Standard screen resolution of 1280 x 1024 is considered for the estimates.
This estimate may get revised if we foresee any major update into requirement and functionality. Also, it needs to be aligned when we receive the final functional specs, wireframes, designs/mockups and backend api specifications
Browser stack considered for estimation: 1. Latest Chrome, Firefox & IE 11 on Windows 7/8.1/10 desktop 2. Safari on MAC
Assets such as mock-ups, styleguide, images, fonts should be provided before development.
Assuming feature that exists in current system are reusable. (like reports)
Integration time would revised time to time as per developers requirement.
Change request time is not considered in this estimate.
Estimation assumes that the application touch-points with backend have been identified and documented.
Please note that buffer time is not considered with respect to any leaves.
For browser compatibility, we will be choosing certain combination of OS and browsers.
First round of testing will be performed on Win 10, Chrome (latest version). Once we have stable builds, we will move to other browsers.